## Overview
Developments to the Medical specialty training and transition to the GP workforce OSiD publication
Data Group, Public Services Delivery Scotland
Date range: | All developments from December 2025 to June 2027
Last updated: | 18th August 2026
Contact: | Datagroup@nes.scot.nhs.uk
All developments relate to the Power BI dashboard.
There are two tabs in the workbook:
In development tab lists all the developments we have planned until 2027 |  | In development
Implemented tab lists all developments that have been implemented in December 2025 and June 2026 publications |  | Implemented
The Planned Developments tab categorises each item into one of two stages:
Discovery: Defining the development and addressing data governance, sourcing, quality, and reporting.
If an item cannot progress - such as failing to satisfy the Code of Practice for Statistics - the workbook will be updated with a specific reason.
In development: Confirmed viable under the Code of Practice for Statistics and actively being built. A provisional or finalised publication release date will be usually provided.

## In development
Item Number | Description | Rationale | Background or further information | Stage of development | Publication release date | Provisional or finalised publication date
6 | Widening the training statistics to include all medical specialties. | Provides a more comprehensive view of the medical training pipeline. This ensures users can access consistent information across specialties and supports specialty-level workforce planning. | Originally planned for release in June 2026, however we had not fully appreciated the scale of the effort needed to quality assure the figures when we produced only the GP figures. We are currently identifying the right educators to consult about the training figures in each specialty. We anticipate having to review the background to the statistics with a number of them, so we will need to allow additional time to ensure we support them properly. | In development | December 2026 | Provisional
7 | Estimate the transition from medical specialty training to NHS Scotland consultant workforce. | Improve the understanding of workforce supply pathways and support medical workforce planning. | Originally planned for release in June 2026, however the link between the training and employment data appears not to be as robust for other specialties as it is for General Practice (which uses a different employment data set). Our preferred unique identifier, GMC number, is not complete across the training and employment data sets, and we will need to investigate alternative methods of record linking to describe the transition from training to the consultant workforce. We will be working with our data engineers to explore and evaluate the options. | Discovery
8 | Report the NHS Scotland consultant workforce by GMC specialty. | NHS Scotland workforce official statistics report the specialty of practice for Consultants. In some cases, this is not the same as the GMC specialty. Providing both statistics improves the range of information available. Requested by users. | https://www.gmc-uk.org/education/standards-guidance-and-curricula/curricula#specialty-curricula | Discovery
9 | Report the Primary Medical Qualification (PMQ) source for the NHS Scotland consultant workforce. | Reporting the source of PMQ provides greater insight into the composition of the medical workforce and the contribution of internationally trained doctors to NHS Scotland. |  | Discovery

## Implemented
Item Number | Description | Rationale | Further information | Publication release date
1 | Inclusion of the mean Whole Time Equivalent of for the NHS Scotland employment. | Provides an average staffing measure, giving users greater insight into workforce resource levels. | https://www.scotmt.scot.nhs.uk/general-practice/programme-information/gp-programme-descriptors/ | 2026-06-30
2 | Option to view the number starting training, number completing training and inflow from specialty registrars charts as a percentage of the total headcount. | Makes it easier for users to switch between absolute values (headcount) and relative measures (percentage) enabling clearer comparison of trends between variables and over time. |  | 2026-06-30
3 | Expanded the duration of training analysis to show the completion probability for any combination of the variables. | Provide greater granularity for users. |  | 2026-06-30
4 | Expanded the transition to the workforce analysis to show the completion probability for any combination of the variables. | Provide greater granularity for users. |  | 2026-06-30
5 | Include 95% confidence intervals in the completion and transition probabilities | Included 95% confidence intervals to provide an indication of the uncertainty around estimates, helping users interpret and compare results more confidently. |  | 2026-06-30